# PGDAY.EU 2009 / 20091021 Meeting
- Location : IRC (#pgday on freenode)
- Date : 2009-10-21 (9pm - 11:30pm)
## People attending the meeting
### on IRC
- Guillaume Lelarge (gleu)
- Andreas Scherbaum (ads)
- Dave Page (pgSnake)
- David Fetter (davidfetter)
- Damien Clochard (daamien)
- Jean-Paul Argudo (jpa)
- Marc Cousin (marco44)
- Guillaume Smet (gsmet)
### People missing
Magnus Hagander
## Agenda of the meeting
- Talks: schedule / speakers
- Badges
- Conference bags and Tshirts
- Poster session for OSOR.eu
- Social events
- Sponsors invitations
## Minutes of the meeting
### Talks: schedule / speakers
No more changes on the schedule, which is really good.
We now have 8 lightning speakers. 1 more would be nice, volunteers are welcome. We didn't receive yet the proposal from objectwiz.
Materials are still lacking for the booklet. Marc Cousin will take care of emailing speakers and bugging them to reduce the length of their bio, abstract, etc. to conform to the new limitations of the booklet. A more urgent message will be sent to speakers. The deadline has been defined: 2009-10-28.
Damien Clochard will finish the booklet design on saturday, 31th.
### Badges
About attendee name badges, Dave Page had comments from Magnus Hagander on this, based on his recent experience at pg west:
- They should be printed.
- Speakers should have a different colour badge to everyone else.
- We should include name and company, but leave a space for people to write irc nicks etc if they want to do so.
Staff also will get badges. Damien Clochard will order the badges. Jean-Paul Argudo will pay them. Andreas Scherbaul will do the printing.
We should try to talk to Gabriele and make him bring the PG necklaces, if he still has some. Andreas Scherbaum sent him an email on this issue.
### Wine
Jean-Paul Argudo contacted a wine producer, based on Gavin Sherry's advices. Here are the results: 7,84 € TTC per bottle, duty and delivery paid. The wine is a Morgon 2007 organic, 75 cl the bottle (3/4 a liter). Talel and Sidonie have no problem with us bringing wine for lunch.
We decided on 84 bottles for the two days. They will be stored in the dev room (which can be locked up) during the two days.
### Conference bags and Tshirts
Damien Clochard will order them tomorrow (2009-10-22).
The bags will be in paper which is a bit more expensive than plastic (http://www.postgresql.fr/en:pgday2009:tshirts_and_polos#bags) but better meets environmental concerns of some of us. The bags are brown, with one colour print.
Better quality is available but with a much higher price (500€ for 200 bags, so over 5 times the price).
### Poster session for OSOR.eu
Everyone on the list seemed to agree for the poster session. So, Dave Page sent an email to Ismael Olea to say we're OK with this.
### Social events
It's not sure we'll do something on sunday. Some of us will probably be available, but not all.
Jean-Paul Argudo is afraid we won't have time to organize a tour like Dan does in Ottawa.
akretschmer and Andreas Scherbaum are in Paris from wednesday (2009-11-04) to wednesday (2009-11-11). David Fetter will arrive on the same day and will also stay some time.
Damien Clochard did not yet confirm with the bar for the party. He wants to do that tomorrow (2009-10-23). As soon as we've got confirmation from the bar, we should update the website's social events page.
### Sponsors invitations
Many think it's too late to make up rules now, except maybe a bulk discount for 15+. The discount is 20% off for 15 or more registrations.
We should extend the registration deadline as well, until 31st October.
## Work to do ASAP
- Guillaume Lelarge
  - Make a proposal for power cables
- Andreas Scherbaum
  - Get in touch with Marko Kreen from Skype
  - Badges' printing
- Magnus Hagander
  - Objectviz's sponsor contrat
- Marc Cousin
  - Email to speakers
- Damien Clochard
  - Finish the booklet design on saturday, 31th
  - Order the badges, bags and tshirts
  - Confirm with the bar for the party
- Jean-Paul Argudo
  - Order the wine.
## Upcoming meetings
2009-10-28