Propaganda

Roadmap

Here's a draft of the schedule for public announcements and other propaganda activities.

Feel free to add any idea

Date	Event / Medium	Lang	Content	Note
Feb 4th	FOSDEM	English	First Announcement + flyers + posters
February	web & mailing lists	English/French	Announcement on pg.org, pg.fr, etc.
March 21	Website infrastructure ready	English
March 30	Website Contents and Translations	English/French/others?
March 30	Solutions Linux (Paris)	French	flyers + posters
May 21	PGCon (Ottawa)	English	flyers + posters
June	web & mailing lists	English/French	Announcing the registration opening
June	web	English/French	Banners on websites
July 7th	RMLL (Nantes)	French	flyers + posters
September 15th	End of “early bird registration”
September 28th	web & mailing lists	English/French	1 month before registration closing
October 26th	web & mailing lists	English/French	1 week before registration closing
October 31th	web & mailing lists	English/French	last chance to register

Material

Banners

work in progress

Small (60×120): Small (60x120)

Medium (180×180): Medium (180x180)

Impact Banner (468×60): Impact Banner (468x60)

Large (120×700): Large (120x700)

Leaderboard (728×90): Leaderboard (728x90)

Eiffelephant Flyer/Poster (french version)

TODO

Eiffelephant Flyer/Poster (english version)

SVG file : http://svn.postgresqlfr.org/repos/materials/events/trunk/pgday.eu_2009/flyers/eiffelephant_v2.svg

EPS files :

A3 : http://wiki.postgresql.fr/_media/en:pgday2009:eiffelephant.a3.eps

A5 : http://wiki.postgresql.fr/_media/en:pgday2009:eiffelephant.a5.eps