Propaganda

Roadmap

Here's a draft of the schedule for public announcements and other propaganda activities.

Feel free to add any idea

Date	Event / Medium	Lang	Content	Note
Feb 4th	FOSDEM	English	First Announcement + flyers + posters	done
February	web & mailing lists	English/French	Announcement on pg.org, pg.fr, etc.	done
March 21	Website infrastructure ready	English	done
March 30	Website Contents and Translations	English/French/italian/others?	done
March 30	Solutions Linux (Paris)	French	flyers + posters	done
May 21	PGCon (Ottawa)	English	flyers + posters	done
June	web & mailing lists	English/French	Announcing the registration opening
June	web	English/French	Banners on websites	done
July 7th	RMLL (Nantes)	French	flyers + posters	too late
September 15th	End of “early bird registration”
September 28th	web & mailing lists	English/French	1 month before registration closing
October 26th	web & mailing lists	English/French	1 week before registration closing
October 31th	web & mailing lists	English/French	last chance to register

Material

Banners

Size	PNG
Small	60×120	Small (60x120)
Medium	180×180	Medium (180x180)
Impact Banner	468×60	Impact Banner (468x60)
Large	120×700	Large (120x700)
Leaderboard	728×90	Leaderboard (728x90)

Eiffelephant Flyer/Poster (french version)

TODO

Eiffelephant Flyer/Poster (english version)

SVG file : http://svn.postgresqlfr.org/repos/materials/events/trunk/pgday.eu_2009/flyers/eiffelephant_v2.svg

EPS files :

A3 : http://wiki.postgresql.fr/_media/en:pgday2009:eiffelephant.a3.eps

A5 : http://wiki.postgresql.fr/_media/en:pgday2009:eiffelephant.a5.eps